## Plan
Task | Owner(s) | Start | End | Duration (days)
Requirements & Regulations Analysis | Kamelia & Ghena | 2026-02-07 | 2026-02-15 | 8
Standards & Criteria Mapping | Kamelia | 2026-02-15 | 2026-02-21 | 6
System Architecture & ERD | Ghena | 2026-02-21 | 2026-02-28 | 7
Database & Schema | Ghena | 2026-02-28 | 2026-03-08 | 8
Auth & Roles (Backend) | Kamelia | 2026-03-08 | 2026-03-16 | 8
Core Entities CRUD (Backend) | Kamelia & Ghena | 2026-03-16 | 2026-03-27 | 11
Frontend Foundations | Kamelia | 2026-03-27 | 2026-04-02 | 6
Forms & Validation (Frontend) | Ghena | 2026-04-02 | 2026-04-10 | 8
Search & Filters | Kamelia & Ghena | 2026-04-10 | 2026-04-16 | 6
Workflow & Automation Rules | Kamelia | 2026-04-16 | 2026-04-24 | 8
Document Management | Ghena | 2026-04-24 | 2026-05-02 | 8
Dashboards & Reports | Kamelia & Ghena | 2026-05-02 | 2026-05-10 | 8
Integration & Security Hardening | Kamelia & Ghena | 2026-05-10 | 2026-05-18 | 8
User Acceptance Testing | Kamelia & Ghena | 2026-05-18 | 2026-05-24 | 6
Deployment & Documentation | Kamelia & Ghena | 2026-05-24 | 2026-06-01 | 8